IRI

INEZA REFUGEES INITIATIVE (IRI)

Donate for Refugees

WORK PLAN AND BUDGET FOR 5 YEARS

2025-2030

- Introduction

Ineza Refugees Initiative  - Uganda is an independent not-for-profit organization incorporated with the Uganda Registration Services Bureau (URSB), under section 18 (3) of the Companies Act 2012, Registration No: 80034850054909.

Development-oriented people who are determined to contribute towards sustainable development by empowering refugees through increasing access to quality and reliable resources and information formed Ineza Refugees Initiative. The organization is based in  Uganda operates in the whole country.

- Goal

Improve Socio-economic transformation and general wellbeing of refugees through research and resource mobilization

- Vision, Mission and Values

Ineza Refugees Initiative is proud to welcome refugees and help them to rebuild their lives.

Our vision

A dignified life for all Refugees in Uganda.

Our Mission

We assist Refugees, protect their rights and empower them towards a better future

Our values

- Inclusive: We are inclusive. We work with all Refugees and people seeking asylum, so they have an equal voice, co-producing projects and ensuring their expertise and experiences are at the heart of what we do.

- Collaborative: We are collaborative, working with Office of the Prime Minister (OPM) and other Refugee NGOs to have a collective impact. We strive for successful and responsible joint efforts with all beneficiaries, donors, partners and others.

- Honesty and transparency: Ineza Refugees Initiative is accountable to the people we help, those that support us, and those with whom we collaborate. We are honest and open about what we do and about the choices we make, and if a situation may exceed our ability to provide help.

- Independence and neutrality: Ineza Refugees Initiative works exclusively on the basis of its mandate towards the Refugees. Ineza Refugees Initiative focuses on issues concerning refugees, remaining strictly neutral when it comes to party politics. This also means that in conflict settings, our humanitarian work is predicated on the principle of independence and neutrality in regard to the conflicting parties.

v) Humanitarian approach: The right to a dignified life takes precedence over politics and principles. Ineza Refugees Initiative insists on the right of the individual to receive humanitarian aid and on our right and duty to provide such aid, whenever possible, regardless of political circumstance.

Objectives:

- To train the most vulnerable families of refugees with basic livelihood skills necessary to empower them participate in their development and self-reliance.

- To educate and support women, single mothers, orphans and abandoned children with elementary knowledge on personal health, sexuality and gender related issues.

- Promote refugees’ wellbeing, mental health and tackling domestic violence.

- Creating economic opportunities to help them to get out of seismic poverty and shortage and to embrace sustainable development.

- To create cohesion between refugees and hosting Refugees via activities that generate common development.

- Empower refugees to be their own advocates on the issues affecting their rights and life.

- To strengthen the capacities of Refugees through action planning and training, improve resilience to disaster, and enable dialogue and collaboration between stakeholders.

- Program areas

To achieve our  objectives and realize our vision , Ineza Refugees Initiative conceptualized five key programmatic areas;

  - Agribusiness and Food Nutrition

Under this program, Ineza Refugees Initiative intends to provide Refugees with knowledge, skills and financial resources to utilize the available agricultural resources and market opportunities to improve their livelihoods. The focus will be on agribusiness development and improving smallholder-farming techniques, with a commitment to transforming Refugees from subsistence to market-oriented farming.

Strategic goal: To promote household agricultural output and food and nutrition security through research, Refugees sensitization and mobilization.

Objectives:

- To provide evidence-based information from production to processing and marketing to distribution of household agricultural resources.

- To facilitate Refugees mobilization on nutrition and nutrition behavioural change communication using ‘Food nutrition champions’

- To empower women and girls to utilize agribusiness opportunities to improve household food and nutrition security

Program activities:

- Baseline survey, including SWOT analysis of agribusiness

- Training in developing agribusiness entrepreneurship and agribusiness value chains

- Situation analysis of nutrition status to identify practicable and sustainable interventions

- Identification and training (seminars and workshops) of Refugees ‘Food nutrition champions’

- Train women and girls on good nutrition practices

Expected outputs:

- Baseline report on agribusiness

- Training curriculum and report

- Trained Food nutrition champions

- Trained women and girls

  - Primary Health Care

This program area will be at the forefront of research on the emerging primary health care services such as child health and safe motherhood. We will generate evidence that leads to stronger and more responsive health systems able to address specific health needs of the vulnerable children. To support build more resilient health systems, our program will address knowledge gaps related to management and delivery of child health and development services at the Refugees level.

Based on evidence generated, Ineza Refugees Initiative will provide basic health care services to the underprivileged children especially those in hard-to-reach areas. We will have a Refugees outreach programme where a Refugees health worker or village health team conducts Refugees meetings or home visits to build awareness about primary health care services like immunization, breastfeeding, child growth monitoring, pregnancy, family planning, health-checkups and counselling. Ineza Refugees Initiative will collaborate with private and public health facilities act as referral centres.

Strategic goal:

To facilitate better access to comprehensive health care services and improve health outcomes

Objectives:

- To provide health education and counselling

- First aid treatment

- Referral for complicated cases

Program activities:

- Baseline survey (KAP) on primary health care services

- Recruitment and training of service providers

- Development of IEC materials

- Refugees sensitization and mobilization

- Conduct Refugees meetings and home visits

- Organize Mother and Child Health Days at health centers

- Conduct Radio and/or TV Talk shows

Expected outputs:

- Number of clients served by type of service

- Recruited and Trained VHTs or CHWs

- Number of clients referred

  - Education

Ineza Refugees Initiative will support primary education children, specifically the most vulnerable children in the hard-to-reach areas. We shall provide tuition (school fees), uniform and scholastic materials like books and pens.

Strategic goal:

To empower children with knowledge and skills to enable them transform their families and Refugees.

Objectives:

- To ensure access to quality primary education to vulnerable children in the hard-to-reach areas

- To increase the  number of children (boys and girls) regularly attending school

Program activities:

- Baseline survey of school-going age children

- Identification of vulnerable children using parents’ interviews, LC and Opinion leaders’ recommendations, and profiling them

- Identification of schools and sign MoUs to support children

- Support children (boys and girls) with tuition, uniform and scholastic materials

Expected outputs:

- Survey report disseminated to all stakeholders

- Number of vulnerable children(boys and girls) supported with tuition, uniform and scholastic materials

- Number of schools participating in the project

- Number of children regularly attending school

  - Youth Empowerment:

Under this program area, Ineza Refugees Initiative will provide youth with opportunities for meaningful involvement in Refugees development. This will involve providing entrepreneurship development and capacity building activities to the youths, while encouraging them to take control of their lives, with adult support. The program will create a positive setting for youth to develop their Refugees.

Strategic goal:

To contribute to the socio-economic transformation of youth by providing youth-led entrepreneurship skills and capacity building services

Objectives:

- To improve youth livelihoods through sustainable  economic activities

- To develop a youth-led entrepreneurship program along the agricultural and food supply chains

- To equip youth with skills to enhance employability and entrepreneurship in small scale businesses

Program activities:

- Baseline survey of youth entrepreneurship

- Mobilization of youths about the potential of youth entrepreneurship programs

- Training of youth in entrepreneurship skills

- Recruitment of peer youth entrepreneurship leaders

- Formation of youth groups or associations to help market youth products and SACCO to encourage saving culture

Expected outputs:

- Baseline report on Youth entrepreneurship

- Youth mobilized and trained

- Peer youth entrepreneurship leaders

- Youth groups or associations formed

- Logical Framework

|  | Objectively Verifiable Indicators | Means of verification | Assumptions/Remarks |
| --- | --- | --- | --- |
| Overall goal: To improve the socio-economic transformation and general wellbeing of the most vulnerable Refugees through research and resource mobilization | Improved socio-economic status of the Refugees | Official statistics from Uganda Bureau of Statistics(UBOS) | - Active participation and buy-in of Refugee Households and other stakeholders in the area of operation - All actors are committed during the implementation of all activities |
| Program area: Agribusiness and food nutrition |  |  |  |
| Objective: To promote household agricultural output and food and nutrition security through research, Refugees sensitization and mobilization | 90% of Refugee Households with increased agricultural productivity and food secure | - Baseline survey - Midterm Household survey - End line program survey | - Active participation and buy-in of Refugee Households and other stakeholders in the area of operation - All actors are committed during the implementation of all activities |
| Outcome: Refugee Households are engaged in agribusiness enterprises | 80% of household engaged in agribusiness enterprises | - Annual reports - Monitoring reports - Household visits | - Active participation and buy-in of Refugee Households and other stakeholders in the area of operation - All actors are committed during the implementation of all activities |
| Outputs: Refugee Households are trained and supported in agribusiness and food nutrition | - 6 training workshops conducted - 300 participants trained in agribusiness and food nutrition - 80% of participants engaged in at least 1 agribusiness enterprise - 70% of Refugee Households adhering to best food nutrition practices - 300 women and girls trained and active Food nutrition champions(FNC) - 60 Food Nutrition Champions trained | - Training reports/records - Attendance Certificates - Household surveys - Monitoring visits - FNC training reports | - Active participation and buy-in of Refugee Households and other stakeholders in the area of operation - All actors (including FNCs) are committed during the implementation of all activities |
| Activities: - Baseline survey, including SWOT analysis of agribusiness; - Training in developing agribusiness entrepreneurship and agribusiness value chains - Situation analysis of nutrition status to identify practicable and sustainable interventions - Identification and training (seminars and workshops) of Refugees ‘Food nutrition champions’ - Train women and girls on good nutrition practices |  |  |  |
| Program area: Primary Health care |  |  |  |
| Objective: To facilitate better access to comprehensive health care services | 10,000 beneficiaries of PHC services | - Baseline survey - Midterm Household survey - End line program survey - Annual reports | - Refugees interest and commitment. - Staff and other actors’ commitment. |
| Outcome: Refugees members benefit from the primary health care services | - 4 trainings of service providers, VHTs or CHWs conducted - 40 Service Providers trained - 6 Radio Talk shows conducted - 6 MCH days conducted - 3,000 referrals conducted | - Training reports - Attendance Certificates - Talk shows reports - Supervision reports - Monitoring reports - MCH Days reports - Referral Cards | - Refugees interest and commitment. - Staff and other actors’ commitment. - Demand and need for the services. - Availability of funds and other resources |
| Outputs: Refugees members attend trainings | - 10 health facilities participating - 3 Radio Stations participating - 50 active VHTs or CHWS - 10,000 IEC materials developed and disseminated | - Training reports - Talk shows reports - Supervision reports - Stock reports | - Refugees interest and commitment. - Staff and other actors’ commitment. - Demand and need for the services. - Availability of funds and other resources |
| Activities: - Baseline survey (KAP) on primary health care services - Recruitment and training of service providers, VHTs or CHWS - Development of IEC materials - Refugees sensitization and mobilization - Organize Mother and Child Health Days - Conduct Radio Talk shows |  |  |  |
| Program area: Education |  |  |  |
| Objective: To ensure access to quality primary education to vulnerable children in the hard-to-reach areas | 95% of Children attending school | - Baseline survey - Interviews from parents, teachers and children - Project evaluation report | Refugees and children are motivated and willing to participate in the project |
| Outcome: To increase the number of children (boys and girls)attending school | - Over 90% of the children (boys and girls) are attending school regularly - Over 90% of Children are enjoying school learning | - School registers - Interviews from teachers and children - Monitoring reports - Supervision reports | - Active participation and commitment of children, teachers and parents - All actors are committed during the implementation of all activities |
| Outputs: - Baseline survey of school-going age children - Children supported with tuition, uniform and scholastic materials - Children regularly attend school - Schools participate in the project | - Baseline survey of school-going age children - 250 vulnerable children (boys and girls) supported with tuition, uniform and scholastic materials - 10 Schools participating in the project | - Survey report - School registers - Interviews from teachers and children - Monitoring reports - Supervision reports | - Active participation and commitment of children, teachers and parents - All actors are committed during the implementation of all activities |
| Activities: - Baseline survey of school-going age children - Identification of vulnerable children using parents’ interviews, LC and Opinion leaders’ recommendations, and profiling them - Identification of schools and sign MoUs to support children - Support children (boys and girls) with tuition, uniform and scholastic materials |  |  |  |
| Program area: Youth Empowerment |  |  |  |
| Objective: To contribute to the socio-economic transformation of youth by providing youth-led entrepreneurship skills and capacity building services | 90% of youth with increased economic productivity | - Baseline survey and SWOT analysis - Midterm Household survey - End line program survey - Annual reports |  |
| Outcome: - Improved entrepreneurship skills - Improved youth employment levels - Reduced youth-led crime - Increased youth engagement in Refugees development | - 200 youth trained in entrepreneurship skills - 200 of youth trained in capacity building skills | - Attendance Certificates - Training reports - Supervision reports - Monitoring reports | - Active participation of youths and other stakeholders in the area of operation - All actors are committed during the implementation of all activities - Availability of funds and other resources |
| Outputs: - Baseline report on Youth entrepreneurship - Youth mobilized - Trained youth - Peer youth entrepreneurship leaders - Youth groups or associations formed | - 10 youth associations and groups - 20 Youth entrepreneurship leaders Number of trainings - 2000 Behavioral change communications(BCC) materials developed and distributed | - Supervision reports - Monitoring reports - Training reports | - Active participation of youths and other stakeholders in the area of operation - All actors are committed during the implementation of all activities - Availability of funds and other resources |
| Activities: - Baseline survey of youth entrepreneurship - Mobilization of youths about the potential of youth entrepreneurship programs through behavioral change communications(BCC) - Training of youth in entrepreneurship skills - Recruitment of peer youth entrepreneurship leaders - Formation of youth groups or associations to help market youth products and SACCO to encourage saving culture |  |  |  |

- Work frame

| Activities | Responsible Person | Years |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- |
|  |  | 1 | 2 | 3 | 4 | 5 |
| Program area 1: Agribusiness and food nutrition (A&F) |  |  |  |  |  |  |
| Baseline survey, including SWOT analysis of agribusiness; | ED | X | X |  |  |  |
| Training in developing agribusiness entrepreneurship and agribusiness value chains | Manager (A&F) |  |  | X |  |  |
| Situation analysis of nutrition status to identify practicable and sustainable interventions | Manager (A&F) | X | X |  |  |  |
| Identification and training of Refugees ‘Food nutrition champions’ | RO |  | X | X |  |  |
| Train women and girls on good nutrition practices | RO |  |  |  | X |  |
| Program area 2: Primary Health Care (PHC) |  |  |  |  |  |  |
| Baseline survey (KAP) on primary health care services | Manager (PHC) | X | X |  |  |  |
| Recruitment and training of service providers | RO |  |  | X |  |  |
| Development of IEC materials | RO |  |  |  | X |  |
| Refugees sensitization and mobilization | RO |  |  |  | X |  |
| Mother and Child Health Days | RO |  |  |  | X |  |
| Program area 3: Education (Educ) |  |  |  |  |  |  |
| Baseline survey of school-going age children | Manager (Educ) | X | X |  |  |  |
| Identification of vulnerable children using parents’ interviews, LC and Opinion leaders | RO |  |  |  | X |  |
| Identification of schools and sign MoUs to support children | Manager |  |  |  | X |  |
| Support children (boys and girls) with tuition, uniform and scholastic materials | RO |  |  |  |  | X |
| Program area 4: Youth Empowerment (YE) |  |  |  |  |  |  |
| Baseline survey of youth entrepreneurship | Manager | X | X |  |  |  |
| Mobilization of youths about the youth entrepreneurship programs | RO |  |  | X |  |  |
| Training of youth in entrepreneurship skills | RO |  |  | X | X |  |
| Recruitment of peer youth entrepreneurship leaders | RO |  |  |  |  |  |
| Formation of youth groups or associations | RO |  |  |  |  |  |
| Monitoring and evaluation | Head of Programs |  |  | X |  | X |
| Documentation and sharing of progress reports | Head of Programs |  |  |  | X | X |

Key:

ED = Executive Director

RO = Refugee Officer

- Budget estimates (Annual)

| Activity | Unit price (UGX) | Quantity | Price (UGX) |
| --- | --- | --- | --- |
| Program area 1: Agribusiness and food nutrition |  |  |  |
| 1.1 Baseline survey, including SWOT analysis of agribusiness; |  |  |  |
| Fuel for preparatory activities | 74,000 | 10 Refugee sites | 740,000 |
| Training of Research Assistants | 92,500 | 10 Allowance and Transport refund) | 925,000 |
| Data Collection | 111,000 | 10 Research Assistants*10 days | 11,100,000 |
| Data entry and cleaning | 1,850,000 | 1 Data manager | 1,850,000 |
| Data analysis & Report writing | 370,000 | 10 Days * 2 staff | 7,400,000 |
| Dissemination of findings | 3,700,000 | 1 day | 3,700,000 |
| Sub Total | 6,197,500 |  | 25,715,000 |
| 1.2 Training in developing agribusiness entrepreneurship and agribusiness value chains |  |  |  |
| Fuel for preparatory activities | 74,000 | 4 Refugee camps * 6 rounds | 4,440,000 |
| Hire of training venue | 129,500 | 2 days * 6 rounds | 1,554,000 |
| Facilitators honorarium | 185,000 | 2 days*3 facilitators * 6 rounds | 6,660,000 |
| Training materials (stationery) | 11,100 | 2 days *50 participants * 6 rounds | 6,660,000 |
| Radio Announcements Airtime | 74,000 | 5 announcements * 6 rounds | 2,220,000 |
| Refreshments & lunch | 18,500 | 2 days*53 participants * 6 rounds | 11,766,000 |
| Transport refund | 37,000 | 50 participants * 6 rounds | 11,100,000 |
| Sub Total | 529,100 |  | 44,400,000 |
| 1.3 Situation analysis of nutrition status to identify practicable and sustainable interventions |  |  |  |
| Training of Research Assistants | 92,500 | 10 Allowance and Transport refund) | 925,000 |
| Data Collection | 111,000 | 10 Research Assistants*5 days | 5,550,000 |
| Data entry and cleaning | 1,850,000 | 1 Data manager | 1,850,000 |
| Data analysis & Report writing | 370,000 | 5 Days * 4 staff | 3,700,000 |
| Dissemination of findings | 2,960,000 | 1 day | 2,960,000 |
| Sub Total | 5,383,500 |  | 14,985,000 |
| 1.4 Identification and training of Refugees Food nutrition champions |  |  |  |
| Fuel for preparatory activities | 74,000 | 4 Refugee camps* 3 rounds | 2,220,000 |
| Hire of training venue or Tents & chairs | 129,500 | 2 days* 3 rounds | 777,000 |
| Facilitators honorarium | 185,000 | 2 days*3 facilitators* 3 rounds | 3,330,000 |
| Training materials (stationery) | 11,100 | 2 days *20 participants* 3 rounds | 1,332,000 |
| Radio Announcements Airtime | 74,000 | 5 announcements* 3 rounds | 1,110,000 |
| Refreshments & lunch | 18,500 | 2 days*23 participants* 3 rounds | 2,553,000 |
| Transport refund | 37,000 | 20 participants* 3 rounds | 2,220,000 |
| Sub Total | 529,100 |  | 13,542,000 |
| 1.5 Train women and girls on good nutrition practices |  |  |  |
| Fuel for preparatory activities | 74,000 | 4 Refugee camps*6 trainings | 4,440,000 |
| Hire of training venue or Tents & chairs | 129,500 | 2 days *6 trainings | 1,554,000 |
| Facilitators honorarium | 185,000 | 2 days*3 facilitators*6 trainings | 6,660,000 |
| Training materials (stationery) | 11,100 | 2 days *50 participants*6 trainings | 6,660,000 |
| Radio Announcements Airtime | 74,000 | 5 announcements*6 trainings | 2,220,000 |
| Refreshments & lunch | 18,500 | 2 days*53 participants*6 trainings | 11,766,000 |
| Transport refund | 37,000 | 50 participants*6 trainings | 11,100,000 |
| Sub total | 529,100 |  | 44,400,000 |
| Program area 2: Primary Health care |  |  |  |
| 2.1 Baseline survey (KAP) on primary health care services |  |  |  |
| Fuel for preparatory activities | 74,000 | 4 Refugee camps Sub counties | 740,000 |
| Training of Research Assistants | 92,500 | 10 Allowance and Transport refund) | 925,000 |
| Hire of training venue | 129,500 | 2 days | 259,000 |
| Data Collection | 111,000 | 10 Research Assistants*5 days | 5,550,000 |
| Data entry and cleaning | 1,850,000 | 1 Data manager | 1,850,000 |
| Data analysis & Report writing | 370,000 | 5 Days * 4 staffs | 3,700,000 |
| Dissemination of findings | 2,960,000 | 1 day | 2,960,000 |
| Sub Total | 5,587,000 |  | 15,984,000 |
| 2.2 Recruitment and training of service providers |  |  |  |
| Fuel for preparatory activities | 74,000 | 4 Refugee camps * 4 trainings | 2,960,000 |
| Hire of training venue | 129,500 | 5 days * 4 trainings | 2,590,000 |
| Facilitators honorarium | 185,000 | 5 days*3 facilitators * 4 trainings | 11,100,000 |
| Training materials | 11,100 | 10 participants * 4 trainings | 444,000 |
| Refreshments & lunch | 18,500 | 5 days*10 participants * 4 trainings | 3,700,000 |
| Transport refund | 37,000 | 10 participants * 4 trainings | 1,480,000 |
| Sub Total | 455,100 |  | 22,274,000 |
| 2.3 Development of IEC materials |  |  |  |
| Brochures, fliers, leaflets, Caps, T-shirts, etc | 7,400 | 5000 copies * 2 rounds | 74,000,000 |
| Sub total |  |  | 20,000 |
| 2.4 Refugees sensitization and mobilization |  |  |  |
| Conduct Radio and/or TV Talk shows | 740,000 | 1 Show per month for 6 months | 4,440,000 |
| Refugees drives | 370,000 | 2 Drives per month for 6 months | 4,440,000 |
| Hire of Public Address System | 370,000 | $100 per month for 6 months | 2,220,000 |
| Sub total | 1,480,000 |  | 11,100,000 |
| 2.5 Mother and Child Health Days |  |  |  |
| Field mobilization activities | 74,000 | 4 Refugee camps*6 rounds | 4,440,000 |
| Radio Announcements Airtime | 74,000 | 5 announcements*6 rounds | 2,220,000 |
| Facilitators honorarium | 185,000 | 1 days*3 facilitators * 6 rounds | 3,330,000 |
| Sub Total |  |  | 9,990,000 |
| Program area 3: Education |  |  |  |
| 3.1 Baseline survey of school-going age children |  |  |  |
| Fuel for preparatory activities | 74,000 | 4 Refugee camps | 740,000 |
| Training of Research Assistants | 92,500 | 10 Allowance and Transport refund) | 925,000 |
| Hire of training venue | 129,500 | 2 days | 259,000 |
| Data Collection | 111,000 | 10 Research Assistants*5 days | 5,550,000 |
| Data entry and cleaning | 1,850,000 | 1 Data manager | 1,850,000 |
| Data analysis & Report writing | 370,000 | 5 Days * 4 staffs | 3,700,000 |
| Dissemination of findings | 2,960,000 | 1 day | 2,960,000 |
| Sub Total |  |  | 15,984,000 |
| 3.2 Identification of vulnerable children using parents’ interviews, LC and Opinion leaders |  |  |  |
| Mobilization activities | 74,000 | 4 Refugee camps * 3 rounds | 2,220,000 |
| Radio Announcements | 74,000 | 5 announcements * 3 rounds | 1,110,000 |
| Facilitators honorarium | 185,000 | 1 days*3 facilitators * 3 rounds | 1,665,000 |
| Hire of meeting venue | 129,500 | 1 day for 3 rounds | 388,500 |
| Sub Total |  |  | 5,383,500 |
| 3.3 Identification of schools and sign MoUs to support children |  |  |  |
| Mobilization activities | 74,000 | 4 Refugee camps | 740,000 |
| Facilitators honorarium | 185,000 | 10 days*2 facilitators | 3,700,000 |
| Sub Total |  |  | 4,440,000 |
| 3.4 Support children (boys and girls) with tuition, uniform and scholastic materials |  |  |  |
| Tuition | 1,110,000 | 150 children and 100 boys | 277,500,000 |
| Shoes (2 pairs per child) | 55,500 | 2 pairs for 250 children | 27,750,000 |
| School uniforms (2 pairs per child) | 74,000 | 2 pairs for 250 children | 37,000,000 |
| School bags (1 per child) | 37,000 | 1 bag for each of 250 children | 9,250,000 |
| Scholastic materials (books, pens, pencils, sets, reams,) | 74,000 | 1 package for each of 250 children | 18,500,000 |
| Sub Total |  |  | 370,000,000 |
| Program area 4: Youth Empowerment |  |  |  |
| 4.1 Baseline survey of youth entrepreneurship |  |  |  |
| Fuel for preparatory activities | 74,000 | 4 Refugee camps | 740,000 |
| Training of Research Assistants | 92,500 | 10 Allowance and Transport refund) | 925,000 |
| Hire of training venue | 129,500 | 2 days | 259,000 |
| Data Collection | 111,000 | 10 Research Assistants*5 days | 5,550,000 |
| Data entry and cleaning | 1,850,000 | 1 Data manager | 1,850,000 |
| Data analysis & Report writing | 370,000 | 5 Days * 4 staffs | 3,700,000 |
| Dissemination of findings | 2,960,000 | 1 day | 2,960,000 |
| Sub Total |  |  | 15,984,000 |
| 4.2 Mobilization of youths about the youth entrepreneurship programs |  |  |  |
| Mobilization activities | 74,000 | 4 Refugee camps *4 rounds | 2,960,000 |
| Radio Announcements | 74,000 | 5 announcements *4 rounds | 1,480,000 |
| Facilitators honorarium | 185,000 | 1 days*3 facilitators * 4 rounds | 2,220,000 |
| Hire of meeting venue or Tents & chairs | 129,500 | 1 day for 4 rounds | 518,000 |
| Sub Total |  |  | 7,178,000 |
| 4.3 Training of youth in entrepreneurship skills |  |  |  |
| Fuel for preparatory activities | 74,000 | 4 Refugee camps*4 rounds | 2,960,000 |
| Hire of training venue | 129,500 | 2 days*4 rounds | 1,036,000 |
| Facilitators honorarium | 185,000 | 2 days*3 facilitators*4 rounds | 1,480,000 |
| Training materials (stationery) | 11,100 | 2 days *50 participants*4 rounds | 4,440,000 |
| Radio Announcements Airtime | 74,000 | 5 announcements*4 rounds | 1,480,000 |
| Refreshments & lunch | 18,500 | 2 days*53 participants*4 rounds | 7,844,000 |
| Transport refund | 37,000 | 50 participants*4 rounds | 7,400,000 |
| Sub Total |  |  | 26,640,000 |
| 4.4 Recruitment of peer youth entrepreneurship leaders |  |  |  |
| Fuel for preparatory activities | 74,000 | 4 Refugee camps*4 rounds | 2,960,000 |
| Facilitators honorarium | 185,000 | 2 days*3 facilitators*4 rounds | 4,440,000 |
| Refreshments for leaders | 18,500 | 2 days*23 participants*4 rounds | 7,844,000 |
| T-Shirts for leaders | 29,600 | 2 pairs for each of 20 leaders*4 rounds | 4,736,000 |
| Sub Total |  |  | 19,980,000 |
| 4.5 Formation of youth groups or associations |  |  |  |
| Fuel for preparatory activities | 74,000 | 4 Refugee camps | 740,000 |
| Facilitators honorarium | 185,000 | 1 days*3 facilitators*10 | 5,550,000 |
| Refreshments for members | 18,500 | 1 days*20 participants*10 | 6,660,000 |
| T-Shirts for members | 29,600 | 2 pairs for each of 20 leaders | 11,840,000 |
| Development of Group SoPs | 18,500 | 25 copies * 10 | 4,625,000 |
| Hire of meeting venue | 129,500 | 1 day *10 | 1,295,000 |
| Behavioral change communications(BCC) materials | 7,400 | 2000 copies * 2 rounds | 29,600,000 |
| Sub Total |  |  | 60,310,000 |
| TOTAL |  |  | 702,574,500 |

| Staff Salaries (Annual) |  |  |
| --- | --- | --- |
|  | Number | Monthly Salary |  | No.of months | Total |
| Executive Director | 1 | 11,000,000 |  | 12 | 132,000,000 |
| Grants and Compliance Manager | 1 | 9,000,000 |  | 12 | 108,000,000 |
| Finance & Administration Manager | 1 | 9,000,000 |  | 12 | 108,000,000 |
| Refugees Programmes Coordinator | 1 | 9,000,000 |  | 12 | 108,000,000 |
| Grants and Compliance Officer | 1 | 7,000,000 |  | 12 | 84,000,000 |
| Accountant | 1 | 7,000,000 |  | 12 | 84,000,000 |
| Refugee Officers | 4 | 7,000,000 |  | 12 | 336,000,000 |
| Refugee Assistant | 4 | 4,500,000 |  | 12 | 216,000,000 |
| Secretary | 5 | 3,500,000 |  | 12 | 210,000,000 |
| Office Attendant | 5 | 2,500,000 |  | 12 | 150,000,000 |
| Driver | 4 | 3,000,000 |  | 12 | 144,000,000 |
| Advisory Council Allowances | 5 | 1,000,000 |  | 12 | 60,000,000 |
| Sub-Total |  |  |  |  | 1,740,000,000 |

Office Requirements/Facilitation

|  | Number | Monthly Rate | No.of months | Total |
| --- | --- | --- | --- | --- |
| Office rent | 5 | 1,800,000 | 12 | 108,000,000 |
| Communication(Telephone & Internet) | 1 | 5,000,000 | 12 | 60,000,000 |
| Utilities(Electricity & Water) | 1 | 3,000,000 | 12 | 36,000,000 |
| Security | 5 | 1,500,000 | 12 | 90,000,000 |
| Legal services (lumpsum) | 1 | 1,300,000 | 12 | 15,600,000 |
| Travel allowances, Monistoring and supervision | 11 | 1,000,000 | 12 | 132,000,000 |
| One off procurement of office Equipment (Dessk top computers, Laptops, printers, scanners, cupboards, Desks, Chairs, etc) -lumpsum | 1 | 1 | 1 | 80,000,000 |
| Field Motocycles | 5 | 5,000,000 |  | 25,000,000 |
| Vehicle hire (lumpsum) | 1 | 6,000,000 | 12 | 72,000,000 |
| Sub-Total |  |  |  | 618,600,000 |

TOTAL (Annual)  = UGX 3,061,174,500

GRAND TOTAL (5 Years) =   UGX 15,305,872,500